## Sheet1
Sprint number	Tasks assigned	Tasks completed	Reasons
Sprint 1	5	4	Design
Sprint 2	10	10	NA
Sprint 3	6	5	Code
Sprint 4	9	9	NA
Sprint 5	8	6	Code
Sprint 6	13	9	Code, Design, Design, Design
Sprint 7	15	10	Design, Design, Design, Code, Code
Sprint 8	16	17	Code
Sprint 9	12	16	Code, Design, Design, Design
Sprint 10	17	18	Code

Sprint Breakdown	Uncompleted Tasks

			Uncompleted tasks
			Design	10
			Code	7
			NA	2
			Total	19

			Design breakdown
			Research	2
			Art	5
			Administration	0
			Presentation	0
			Design Document	3
Design Tasks Breakdown	Art Breakdown

			UI Art	1
			3D Modeling Planets	2
			3D Modeling Vanity items	2